# COMP 9500 Weekly Progress Update

Progress through 13 October 2026  |  Vancouver time

Vibhor Malik  |  Dr Borna Noureddin

Experiment 1 remains complete in the project records. Formal Experiment 2 remains pending. I reported 13 active hours for October 5 to 11, including 2 hours of independent work after the meeting was skipped. Week 2 work remains outstanding and actual hours are unreported. This update reconciles progress with the October 4 plan. [1, 2]

# Verified evidence and prepared support

The October 11 evidence review recovered the final October 4 report and plan and checked their match to the final Git update package. The recovered research archive matched the handoff SHA-256. These earlier checks remain the evidence baseline. [1, 2, 4]

The October 4 documentation baseline remains commit e307002 on main. Today’s safe-engineering changes were pushed as commit 7ab27c2 on codex/oct13-safe-engineering, with main unchanged. The public repository remains a partial review copy; supervisor access and full-evidence handoff still need confirmation. [3, 4, 13]

Today’s cloud and local checks each matched all 288 frozen E1 file hashes. The local manifest-only verifier found no mismatches or missing files. The September 29 E2 commitment timestamp is preserved. The checklist records the separate runs, methods and execution boundaries. [11, 12, 13]

The evidence checklist, claim map, primary-source notes, 100-row worked-practice CSV and 22-page answer guide are ready. The checklist now maps each Week 2 task to its status, required evidence and next step.

# What the existing experiment supports

The October 4 report records 865 users and 2,593 items. Target-category proportion rises from 11.6% to 79.2%; muted-category exposure falls from 6.1% to zero through deterministic exclusion. Llama and the rule parser produce identical feeds on the templated ranking task. Broader synthetic parsing scores 79/100, below the 85% target, and boost NDCG@10 falls 45.7%. These historical findings support bounded category control and its costs, without establishing an LLM ranking advantage or improved recommendation accuracy. [2]

Today’s recount confirmed 2,009 full-ranking and 5,190 request-score hash differences in historical logs. Their cause remains unresolved; missing original score vectors prevent quantifying numerical error. The earlier audit reproduced 25,950 top-10 lists. Full model execution and replay on Windows and Colab remain unverified. [2, 12]

# Week 1 status

The 13 hours reported for October 5 to 11 cover scope, evidence and handoff review, plus independent work in place of the skipped meeting. The checklist retains the self-reported 3/3/2/3/2-hour allocation. Repository access and feedback dates still need confirmation. [1, 7]

# Week 2 status against the October 4 plan

October 12 to 18 has a 12-hour planned budget: sources 3 hours, eligible annotation 6 hours, syntax checks 1 hour and supervision 2 hours. Those outstanding tasks remain pending. Actual hours and completed reading and annotation records have not been supplied. [1]

The current 100-question bank is practice. The formal evaluation route and replacement bank still need Borna’s prospective approval. The checklist’s Methods and provenance note records the bank’s status and the requirements for a valid formal study. [5, 9]

The October 23 readiness decision remains pending. The cloud comparison found 15 matching dependency versions, 18 differing and 9 missing. Locally, the earlier 48-test synthetic run passed with one archive-dependent test deselected; seven new manifest-verifier tests passed separately. The local Ollama 0.34.0 client is installed; its local API was unreachable during the check. H1/H2 remain unassessed and H3 has not run. [2, 9, 12, 13]

# Decisions and next steps

Complete the source reading and retain dated notes. The checklist identifies the passages, questions and evidence to record.

Agree the prospective formal evaluation method and replacement bank with Borna, then document the execution decision.

Use the separate cloud and local dependency records to complete permitted runtime recovery. The mismatch counts are confirmed; their cause and numerical magnitude remain unresolved. Formal execution still needs the approved method and verified runtime.

Confirm repository access, scope and approval route, paper format, the final deadline, November 27 draft feedback timing and the proposed October 14 check-in.

The plan calls for a Tuesday 10:00 am Vancouver update and Wednesday 10:00 am check-in, subject to the actual invitation. October 13 is the planned update date; sending is not recorded. The October 14 meeting is prospective. December 18 remains a provisional planning target. [8, 9]

# Evidence links

[3] Published October 5 UTC documentation commit

[4] Repository and archive handoff

[5] Annotation procedure

[6] Academic use and student responsibilities

[7] Week 1 update and evidence requirements

[8] Supervisor decisions and risks

[9] Current completion plan

Sources [1] and [2]: final October 4 Word plan and report, filenames ending (2). Sources [11] and [12]: October 11 and October 13 cloud evidence. Source [13]: October 13 local verification and safe-engineering commit 7ab27c2, linked in the checklist.