# COMP 9500 prospective 135 hour completion and verification plan

Student: Vibhor Malik

Supervisor: Dr Borna Noureddin

Prepared: 2 October 2026, Vancouver time (3 October 2026 UTC)

Planning window: 5 October to 18 December 2026

Status: Proposed schedule. December 2026 is the student's selected target; 18 December is a provisional planning date, not a confirmed course deadline.

The project already has code, recorded Experiment 1 results and draft research artifacts. This plan allocates 135 future active student hours to understanding, checking, completing and improving that work with the supervisor. It is not a claim that 135 hours have been worked, that the student manually produced every artifact, or that Experiment 2 is complete. Agent work and unattended machine runtime do not count as student hours. Actual dates, effort and evidence will be entered only after the work occurs.

The course is 15 weeks and approximately 135 hours. Eleven calendar weeks remain in this proposed window. This plan therefore uses twelve hours in eight weeks and thirteen hours in three weeks: 8 × 12 + 3 × 13 = 135 hours. It does not retrospectively fill the earlier course weeks. The supervisor should confirm that this remaining-term allocation and the December deadline are appropriate.

# Weekly working pattern

A normal 12-hour week can use Monday, Tuesday, Thursday and Friday evenings for two hours each, Wednesday for 1.5 hours plus the 30-minute supervision meeting, and Saturday for two hours. Add one hour in weeks 1, 6 and 11. Weeks 1 to 10 run Monday to Sunday. In the final week, move the normal Saturday allocation into evenings before the provisional Friday deadline. Shift sessions as needed, keeping the weekly budget visible. The update, meeting and minutes together receive two hours within each week's total; they are not additional hours.

The individual meeting transcript agrees on Wednesdays at 10:00 am for about 30 minutes, subject to the supervisor's recurring invitation and any adjustment for the other student. Send the update by Tuesday at 10:00 am, at least 24 hours beforehand. Prepare minutes after each actual meeting, ideally that day. All dates below use America/Vancouver, including the change in UTC offset. Nothing here sends an email, grants repository access or creates an accepted meeting. Check all dates against the institution's calendar, including whether the proposed November 11 slot needs moving.

# Dated work and evidence

| Week | Dates | Hours | Main work | Evidence to retain |
| --- | --- | --- | --- | --- |
| 1 | 05 Oct to 11 Oct | 13 | Confirm scope, ownership and the completion plan. | Scope decision record, exposure declaration, repository handoff checklist. |
| 2 | 12 Oct to 18 Oct | 12 | Read the evidence and complete eligible annotation. | Reading log; genuine completed student sheet and receipt only if actually completed. |
| 3 | 19 Oct to 25 Oct | 12 | Agreement, adjudication and runtime readiness. | Agreement record, preserved label passes, adjudication record, real runtime evidence and gate status. |
| 4 | 26 Oct to 01 Nov | 12 | Reserved evaluation, only if the gates pass. | One-time opening record, complete parser cache, ranking rows and execution logs, or a precise blocked status. |
| 5 | 02 Nov to 08 Nov | 12 | Analyse intended control and quality cost. | Statistics with denominators, intervals, BH-adjusted values and an explicit hypothesis decision table. |
| 6 | 09 Nov to 15 Nov | 13 | Reproduce the implementation and app. | Commands, logs, build diff, browser checklist and explicit platform status. |
| 7 | 16 Nov to 22 Nov | 12 | Independent numerical and claims review. | Cold reports, response log, numerical traceability and revised claims. |
| 8 | 23 Nov to 29 Nov | 12 | Write the complete research argument. | Complete IEEE/ACM LaTeX draft within the course page range and a claim-to-evidence table. |
| 9 | 30 Nov to 06 Dec | 12 | Apply supervisor feedback and finish artifact documentation. | Revised paper, official-template slides, repository access evidence and answered review items. |
| 10 | 07 Dec to 13 Dec | 12 | Rehearse and complete release verification. | Timed rehearsal notes, final cold-review responses and a candidate release fingerprint. |
| 11 | 14 Dec to 18 Dec | 13 | Final review, submission and handoff. | Final release, actual work log, genuine submission receipt and remaining-limitations statement. |
| Total | 5 October to 18 December | 135 | Prospective active student work. | Actual work remains to be logged. |

# Task budgets

Week 1, 13 hours: Review the E1 conclusion and proposal departures (3 h); inspect provenance and the existing E2 commitment without reserved wording (3 h); review AI disclosure and annotation exposure (2 h); prepare private repository handoff (3 h); update, meeting and minutes (2 h).

Week 2, 12 hours: Read primary sources and verify claim boundaries (3 h); complete genuine independent student annotation if eligible (6 h); check worksheet syntax without generating labels (1 h); update, meeting and minutes (2 h).

Week 3, 12 hours: Compare independent labels and report pre-adjudication agreement (3 h); blinded adjudication and evidence preservation (3 h); verify the existing parser commitment and full-freeze prerequisites (2 h); restore and verify the recorded Ollama model on a suitable machine (2 h); update, meeting and minutes (2 h).

Week 4, 12 hours: Verify full-freeze inputs and provenance (2 h); run and actively monitor reserved parsing (2 h); report parser accuracy before ranking (2 h); run ranking and inspect completeness (4 h); update, meeting and minutes (2 h).

Week 5, 12 hours: Recompute H1 by class and pooled plus H2 under the prespecified 11-test family (4 h); compute paired quality estimates and user-bootstrap intervals (3 h); inspect impossible and already-satisfied cases without replacing the primary analysis (3 h); update, meeting and minutes (2 h).

Week 6, 13 hours: Run a fresh environment from a path with a space and relocated server (3 h); inspect frontend rebuild and browser acceptance (3 h); replay committed evidence and distinguish replay from fresh inference (3 h); resolve engineering findings without changing frozen methods (2 h); update, meeting and minutes (2 h).

Week 7, 12 hours: Prepare a self-contained release for cold review (2 h); personally recompute selected high-risk numbers (3 h); respond to numerical and claims findings with evidence (3 h); audit citations and experiment separation (2 h); update, meeting and minutes (2 h).

Week 8, 12 hours: Revise the paper with supported results or explicit pending status (5 h); review related work and the contribution boundary (3 h); verify abstract length, figures, captions and references (2 h); update, meeting and minutes (2 h).

Week 9, 12 hours: Apply recorded feedback to paper and documentation (4 h); clean private repository documentation and reproduction instructions (3 h); complete the supplied BCIT presentation template and speaker notes (3 h); update, meeting and minutes (2 h).

Week 10, 12 hours: Rehearse a 20 to 25 minute talk and 10 to 15 minute question session (4 h); run final archive, release and isolated replay checks where evidence permits (3 h); resolve remaining factual or packaging findings (3 h); update, meeting and minutes (2 h).

Week 11, 13 hours: Apply final agreed corrections (3 h); verify release hashes and all five assessment components (3 h); practise questions and the demo recovery path (3 h); submit approved artifacts and retain actual submission receipt (2 h); update, meeting and minutes (2 h).

# Relationship to the 15-week course structure

| Course phase | Course weeks | Remaining work covered here |
| --- | --- | --- |
| Initiation, literature and design | 1 to 5 | Completion-plan weeks 1 to 3 revisit scope, sources, provenance and the existing committed design. Their existence is not evidence of earlier student work. |
| Implementation | 6 to 10 | Completion-plan weeks 3 to 6 verify runtime, gates, execution and the existing implementation. Frozen experimental methods remain unchanged. |
| Evaluation | 11 to 12 | Completion-plan weeks 4 to 7 cover the gated study, analysis and independent review. |
| Report writing | 13 to 14 | Completion-plan weeks 8 to 9 develop the final argument and apply feedback. |
| Submission and presentation | 15 | Completion-plan weeks 10 to 11 cover rehearsal, release checks and actual submission. |

This is a mapping of remaining tasks to the course phases, not a claim that eleven weeks replace the registered fifteen-week course or that any milestone has been approved.

# Scientific gates and delay policy

Experiment 1 is finished. Preserve its frozen data, models, prompts, gold labels, data/parser_test.jsonl and results. Replay can verify evidence but cannot make the exposed test untouched again. The existing Experiment 2 parser commitment is dated 2026-09-29T05:32:37.866606+00:00. Verify it rather than creating a new timestamp or developing again on this bank.

Experiment 2 is currently blocked: the genuine independent student annotation is missing, and the current environment has no available Ollama runtime. The reserved test has no parser or ranking results. H1 and H2 are not assessed; H3 has not run and is descriptive. An AI may help validate JSON syntax but may not supply the student's labels, identity, attestation or invented annotation times.

Use annotation-handoff.md to record exposure before accessing the annotation-only pack. Before annotation, the student must truthfully record any prior access to reserved wording, author labels, parser implementation, predictions or accuracy summaries and follow the rubric's eligibility conditions. Existing reports have already shown development summaries. Do not sign an independence statement without checking what was actually viewed. If exposure compromises the required pass, keep this study blocked and discuss a separately identified prospective study with fresh material where required. A conversation with the supervisor does not retroactively repair blinding or permit a false receipt.

The required sequence is: verify the existing parser commitment; genuine eligible student annotation; agreement before adjudication; adjudication blinded to model predictions; full freeze; verified Llama 3.1 8B runtime; one reserved evaluation; parser accuracy before ranking results. Retain unsuccessful attempts. Do not tune prompts, rules, policy, metric bands or hypotheses from reserved wording or outcomes. Follow experiment2-runbook.md for the precise stage commands and receipts.

If any gate prevents weeks 2 to 5, use that week's existing hours for primary-source reading, Experiment 1 evidence tracing, reproducibility checks, paper clarity or presentation practice. Record the reallocation in the decision register. Keep Experiment 2 pending and move its dependent work only after the supervisor agrees a feasible schedule within the remaining budget. Do not promise delayed work at zero hours. If H1 or H2 eventually fails, report that natural-language feedback did not demonstrate an expressiveness advantage under this protocol, identifying the failed comparison.

# Evidence and assessment

Use supervision/README.md for the dated update and minutes files, the blank actual-hours log, and the five-component assessment matrix. Weekly templates contain planned prompts, not completed activities or supervisor decisions. Retain verbatim cold-review reports. Their authors' time does not belong in the student's 135-hour log.

The official BCIT presentation template and logo have now been supplied. Template availability does not establish supervisor approval of the research or completion of the presentation. Confirm the IEEE or ACM report format, final deadline, revised scope, research path and AI disclosure. Discuss the original Experiment 1 NI wording: the absolute-margin numerical pass is uninformative at this baseline, and the relative-margin interpretation is unsupported. Experiment 2 makes no NI claim.

The course email specifies a 6 to 10 page LaTeX paper, a 150 to 250 word abstract, and a 20 to 25 minute presentation plus 10 to 15 minutes for questions. Windows and Google Colab remain unverified until actually checked. Academic completion and publication readiness require the supervisor's judgment and evidence beyond software test passes.